## Slide 1: Make Span Schedule
A project has n tasks 1,. . ., n. Task i has duration d(i) to be completed (i=1,. . ., n). There are precedence constraints between tasks represented by a set Q of pairs: for each (i,j) in Q, task j cannot be started before the completion of task i. Compute the earliest completion time of the project.
Input
Line 1: contains n and m (1 <= n <= 104, 1 <= m <= 200000)
Line 2: contains d(1),. . ., d(n) (1 <= d(i) <= 1000)
Line i+3 (i=1,. . ., m) : contains i and j : task j cannot be started to execute before the completion of task i
Output
Write the earliest completion time of the project.

## Slide 2: Make Span Schedule
Input
9 13
5 3 1 2 6 4 3 1 4
1 3
1 5
1 6
2 1
2 3
3 5
4 1
4 2
4 6
5 8
7 9
9 5
9 8
Output
18

## Slide 3: Make Span Schedule
Algorithm
  L is the TOPO list of nodes of G
  F[u]: earlest time point the task u can start
  Explore L from left to right, for each node u:
    makespan = max(makespan, F[u] + d[u])
    For each arc (u,v), update F[v] = max(F[v], F[u] + d[u])
4
2
1
6
3
5
9
7
8
2
2
2
3
3
5
5
5
4
4
6
3
1

## Slide 4: Implementation – Make Span Schedule
#include <bits/stdc++.h>
using namespace std;
const int N = 1e6;
struct Arc{
int v;
int w;
Arc(int _v, int _w): v(_v), w(_w){}
};
int n,m;
int duration[N];
vector<Arc> A[N];// A[v] set of outgoing arc of v
int d[N];// incoming degree
vector<int> L;
int F[N];// F[v] earliest possible starting time-point
int ans;

## Slide 5: Implementation – Make Span Schedule
void input(){
memset(d,0,sizeof d);
cin >>n >> m;
for(int i = 1; i <= n; i++)
cin >> duration[i];
for(int k = 1; k <= m; k++){
int u,v;
cin >> u >> v;
A[u].push_back(Arc(v,duration[u]));
d[v]++;
}
}

## Slide 6: Implementation – Make Span Schedule
void topoSort(){
queue<int> Q;
for(int v = 1; v <= n; v++) if(d[v] == 0)
Q.push(v);
while(!Q.empty()){
int x = Q.front(); Q.pop();
L.push_back(x);
for(int i = 0; i < A[x].size(); i++){
int y = A[x][i].v;
int w = A[x][i].w;
d[y] -= 1;
if(d[y] == 0) Q.push(y);
}
}
}

## Slide 7: Implementation – Make Span Schedule
void solve(){
memset(F,0,sizeof F);
ans = 0;
for(int i = 0; i < L.size(); i++){
int u = L[i];
ans = max(ans,F[u] + duration[u]);
for(int j = 0; j < A[u].size(); j++){
int v = A[u][j].v;
int w = A[u][j].w;
F[v] = max(F[v],F[u] + w);
}
}
cout << ans << endl;
}
int main(){
input();
topoSort();
solve();
}